## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Discussion about Project Workflow | MUST HAVE | Dask implementation | Gogula Avinash Kumar | 3- Completed
S3 | S3 | US-001 | Understanding the workings of dask | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S4 | S4 | US-001 | Github repository setup , Virtual environment configuration | MUST HAVE | Github | Gogula Avinash Kumar | 3- Completed
S5 | S5 | US-001 | Project overview , goals and dask cluster setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S6 | S6 | US-001 | Setting up of Project root folder structure | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S7 | S7 | US-001 | Implementation of Client and Cluster | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S8 | S8 | US-001 | Local Cluster Setup | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S9 | S9 | US-001 | Discussion on schema and implementation of schema | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S10 | S10 | US-001 | Log data processing pipeline implementation | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S11 | S11 | US-001 | Regex implementation | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S12 | S12 | US-001 | Evaluating milestone one and viva | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S13 | S13 | US-001 | Discussion on Module 2 workflow | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S14 | S14 | US-001 | Discussion on Anomaly detection | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S15 | S15 | US-001 | Implementation of Alert system and Discussion on types of anamoly detection, alerts and smtp | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S16 | S16 | US-001 | Discussion on alert,port number,status code | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S17 | S17 | US-001 | Calculating Z score | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S18 | S18 | US-001 | Anomaly Detection Code | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S19 | S19 | US-001 | Explanation for anomaly detection code | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S20 | S20 | US-001 | Project, Sprint, and Document Review | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S21 | S21 | US-001 | Discussed the functionality and implementation of log generation | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S22 | S22 | US-001 | Generating and collecting log data | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S23 | S23 | US-001 | Discussion on Streamlit | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S24 | S24 | US-001 | Discussed Streamlit components and Plotly | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S25 | S25 | US-001 | Implementing Streamlit Dashboard | MUST HAVE | VS code | Gogula Avinash Kumar | 3- Completed
S26 | S26 | US-001 | Added MIT License to the project | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S27 | S27 | US-001 | Fixed errors in the code. | SHOULD HAVE | VS code | Gogula Avinash Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | Task-01 | Virtual environment | 2026-02-05 | 2026-02-05 | Aaron Thomas | Exploring how to implement venv | Completed
US-001 | Task-02 | Regular expression | 2026-02-06 | 2026-02-06 | Aaron Thomas | Use of regex in python | Completed
US-001 | Task-03 | Strip and groupdict | 2026-02-12 | 2026-02-12 | Aaron Thomas | Use of strip and groupdict in python | Completed
US-001 | Task-04 | Ray | 2026-02-13 | 2026-02-13 | Aaron Thomas | Why is ray used ? | Completed
US-001 | Task-05 | Metadata | 2026-02-24 | 2026-02-24 | Aaron Thomas | Understanding metadata concept | Completed
US-001 | Task-06 | Json data | 2026-02-26 | 2026-02-26 | Aaron Thomas | Use of json | Completed
US-001 | Task-07 | email config | 2026-02-26 | 2026-02-26 | Aaron Thomas | creating our own code for email config | Completed
US-001 | Task-08 | Port number | 2026-03-04 | 2026-03-04 | Aaron Thomas | Use of port number | Completed
US-001 | Task-09 | Different types of compenents in Streamlit | 2026-03-05 | 2026-03-05 | Aaron Thomas | Exploring different components in streamlit | Completed
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 19 | Milestone 1 review | project execution and viva
Sprint 2 | Day 26 | Milestone 2 review | project execution and milestone 2 document
Sprint 3 | Day 33 | Milestone 3 review | implementing email config to send email when alert occurs
Sprint 4 | Day 40 | Milestone 4 review | project execution and clearing errors

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7